## Open-B&I
CR # | Ticket # | Issue Open Date | Title | Functional Area | CR Type | Description | Business Driver | Agency Requested | Hour Estimate
| CS0023035 | 2022-07-08 | Request to Include Fiscal Year Field on Requisitions | Requisitions | 3rd-Party | The Fiscal Year field was not included in the field migration to Ariba on Demand. This request is to include the Fiscal Year field on Requisitions in AOD. | Agency Requested | DEO
| CS0025024 | 2022-07-18 | Request to Submit Additional eForms Before Being Redirected to Home Page | User Functions | 3rd-Party | Currently after submission of the User Maintenance eForm the user is redirected to the AOD home page. This request is to allow the option to submit an additional eForm before being redirected to the home page. | Agency Requested | DOH
| CS0025890 | 2022-07-12 | Update Receipt Approval Notification to Prevent Premature Approvals | Notifications | 3rd-Party | AOD functionality creates receipts once a purchase order has been generated in AOD. At this point, an approval notification Email is sent to the requester. The language contained within the Email is prompting users to receive orders immediately, leading to orders being received prematurely. This request is to update the language used within the Email notification. | Agency Requested | DEP
| CS0028838 | 2022-08-03 | Request to Include Invoice Field Within Receipt | Receipts | 3rd-Party | This request is to include a field within the Receipt of a purchase order for the user to specify which invoice the receipt is tied to, if necessary. Invoices are not required in order to receive a purchase order, but the inclusion of this optional field will provide increased visibility for approvers. | Agency Requested | DOT
| CS0026319 | 2022-07-14 | Re-generate Approval Flow for Change Orders with Accounting Update | Requisitions | 3rd-Party | Currently the Approval Flow on a Requisition will only re-generate on a change order if updates are made to one of the following fields - Total Cost, Commodity Code, Requester, Bill To Address, Deliver To Address, Ship To Address, Shipping Method, Delay Purchase Until, Need by Date, FOB Code, and Site Code. | Agency Requested | AHCA
| CS0030955 | 2022-08-16 | Request to display accounting code descriptions when viewing line item | Requisitions | 3rd-Party | When viewing accounting codes for a line item in AOD, you must select the code in order to see the description for the value. This request is to display the description of the code when viewing the line item. | Agency Requested | HSMV
| CS0032824 | 2022-08-29 | Request to remain editing requisition upon clicking Save | Requisitions | 3rd-Party | Currently, when a user selects the Save button when editing a requisition, the user will be rerouted back to the homepage. This request is to allow the user to remain in the PR upon clicking Save so that they may continue to edit the order. | Agency Requested | HSMV
| CS0032918 | 2022-08-29 | Transaction Fee Exemption Code Updates | Requisitions | MFMP-controlled | Request to update the Transaction Fee Exemption Codes in MFMP. | DMS Requested | DMS
| CS0033701 | 2022-09-06 | Request to return to IR approval flow after encountering Insufficient Available Balance error from FLAIR | Invoice Reconciliations | 3rd-Party | Currently it is expected behavior in AOD for an IR to moved to a Rejected status after encountering an error with FLAIR. DFS has requested that if an IR has encountered an Insufficient Available Balance error from FLAIR error, that the IR is not rejected but instead returned back to the approval flow. | Agency Requested | DFS
| CS0030950 | 2022-09-27 | Request to include Encumbrance Number on line item accounting | Requisitions | 3rd-Party | The current functionality for encumbrances in AOD is to not assign the encumbrance number until after the requisition has been fully approved and has processed successfully through FLAIR. This request is to assign the Encumbrance Number for the requisition upon submission of the order, and to display the value within an 'Encumbrance Number' field within the line item accounting details. | Agency Requested | HSMV
| CS0036704 | 2022-09-28 | Request to add Last/Current Approver to available reporting options for Requisitions in AOD | MFMP Standard Reports | 3rd-Party | The Last/Current Approver field of a Requisition is currently not an available field for selection within the MFMP Standard Reports in AOD. This request is to add this field to the list of reportable options. | Agency Requested | DEP
| CS0029115 | 2022-08-04 | Add additional accounting fields to PR approval Email | Notifications | 3rd-Party | This request is to add the Object Code and Organization Code details for line items within the requisition approval Email notification that is sent to approvers. | DMS Requested | DMS
| CS0037922 | 2022-10-07 | Allow columns to be sorted within 'Select Address' Popup of Address Maintenance eForm | User Maintenance | 3rd-Party | Currently, when selecting a Ship To and Bill To address on the Address Maintenance eForm only the Name and ID of the address location is shown, and the user is unable to sort these values. This request is to allow the address popup to be sorted by the column headers available. | Agency Requested | DOH
| CS0025481 | 2022-09-29 | Request to link State Contract ID to DMS State Contracts and Agreements webpage | User Functions | 3rd-Party | In legacy MFMP, upon selecting the State Contract ID of a line item the user would be brought to the corresponding contract page within the DMS State Contract and Agreements website. This request is to implement this functionality within AOD. | Agency Requested | DOT
| CS0038222 | 2022-10-11 | Request to allow DOT Encumbrance Number and DOT Encumbrance Line Number to be editable on a change order | Requisitions | 3rd-Party | Current AOD functionality does not allow the DOT Encumbrance Number or DOT Encumbrance Line Number to be editable on a change order. This request is to allow DOT users to edit these fields when creating a change order. | Agency Requested | DOT
| CS0038371 | 2022-10-11 | Request to trigger 'User To Notify' watcher node if it is changed during approval. | Requisitions | MFMP-controlled | Current AOD functionality only triggers the 'User to Notify' watcher node if it is specified within the original submission of the requisition. This request is to trigger the watcher node if the user is changed during approval. | Agency Requested | DCF
| CS0038558 | 2022-10-12 | Request to view transaction data from additional agencies in AOD | User Functions | 3rd-Party | Current AOD functionality only allows agency customers the ability to view and approve transactions from within their own agency. This request is to allow customers the ability to view data such as requisitions, purchase orders, and contracts, that are outside of their agency. | Agency Requested | HSMV
| CS0042839 | 2022-11-29 | Request to assign substatus to requisition | Requisitions | 3rd-Party | Currently, preprogrammed approval statuses are shown for a requisition (Submitted, Ordered, etc). This request is to include an 'Add status' link on a requisition, which will give customers the option to note a substatus. This will allow customers the ability to specify why a requisition may be in a certain status for an extended period of time. | Agency Requested | DOT
| CS0043593 | 2022-12-13 | Request to allow change order if PO has been invoiced against | Requisitions | MFMP-controlled | Current AOD functionality does not support performing a change order where the PO has been received and invoiced against. This request is to provide customers with the ability to change an order even if it has been received or invoiced. | Agency Requested | HSMV
| CS0043934 | 2022-12-07 | Request to send Email notification to requester when comment is added to an IR | Notifications | 3rd-Party | Current AOD functionality does not notify users when comments are added to an IR, unless the comment is tied to the rejection or approval of the transaction. This request is to add functionality to send a notification to the requester when a comment is added to the IR, when it is not related to the approval/rejection of the transaction. | Agency Requested | FWC
| CS0047469 | 2022-01-04 | Request to add Supplier Search by FEIN to Notification eForm | User Functions | 3rd-Party | Current AOD functionality only allows users creating a Notification eForm to search for a vendor registration by Company Name or by a Vendor ID generated by the VIP application. As a result, the returned results may have identical or similar names, and different IDs. Given that the Vendor ID and Vendor Tax ID values are different, it may be unclear as to which search result should be selected in scenarios where a Vendor has multiple FEINs across multiple registrations. This request is to add the a new FEIN field to the Search criteria for vendor selection on the Notification eForm. | DMS Requested | DMS
| CS0047573 | 2023-01-05 | Request to provide an alternative username if the username already exists in the system | User Maintenance | 3rd-Party | When creating a new user via the User Maintenance eForm, if a username already exists then a "User ID already exist" error message will be shown. This request is to have the system provide an alternate username if this error is encountered. | Agency Requested | FWC
| CS0053087 | 2023-02-15 | Request to provide the option of manually added approvers appearing in future change order approval flows | Requisitions | 3rd-Party | If an approver is manually added to a requisition approval flow while in Composing status, Ariba functionality will continue to add this approver in the flow for future versions. This request is to give the option to turn this configuration off or on within our AOD instance. | Agency Requested | DEP
| CS0052737 | 2023-02-14 | Request to search for User Maintenance eForm by Name of user | User Functions | 3rd-Party | This request is to add Name within the advanced search filter options when searching for a User Maintenance eForm in AOD. This field would correspond to the Name field of the user noted within the eForm. | Agency Requested | DOH
| CS0053799 | 2023-02-22 | Request to search by supplier location when searching for PRs or POs in AOD | User Functions | 3rd-Party | This request is to add the Supplier Location as an advanced search filter option when searching for a Requisition or Purchase Order in AOD. This field would correspond to the Contact field noted for the supplier on the line item of the order. | Agency Requested | DEP
| CS0048742 | 2023-03-27 | Request to add field on requisitions to track orders which involve sharing HIPAA/PHI data with vendors | Requisitions | 3rd-Party | This request is to add a checkbox on the header level of requisitions which can be used to indicate that HIPAA/PHI data is shared with vendors. This will be used for tracking and monitoring purposes. | Agency Requested | AHCA
| CS0056731 | 2023-03-30 | Request to disable the PO Received Quantity Variance exception on invoices for service items | Invoice Reconciliations | 3rd-Party | This request is to bypass the PO Received Quantity Variance exception if the invoice is against a service-based PO. The purpose of this request is to increase efficiency for agencies where a receipt is not required to be submitted against a PO for a service. | DMS Requested | DMS
| CS0070033 | 2023-06-21 | Request to increase AOD attachment file size to 100 MB | User Functions | MFMP-controlled | This request is to increase the file size for AOD attachments. Right now it is currently set to a maximum file size of 25000 KB, and larger attachments are not able to be uploaded. The default size value is 102400 KB. | Agency Requested | DEP
| CS0074476 | 2023-07-25 | Request to update AOD User Delegation Export Interface to include delegations set via User Profile updates. | User Maintenance | MFMP-controlled | Currently, only User Delegations established via the Delegation of Authority eForm are exported from AOD to Tableau. This enhancement will require updates to the interface which exports user delegation information to include self-service delegations established via User Profile changes in AOD. | DMS Requested | DMS
| CS0074530 | 2023-07-25 | Request to Update User Profile System Search to Exclude Supplier Profile Updates | User Maintenance | 3rd-Party | When performing a system search for type User Profile, supplier updates are displayed in addition to user profile updates. Currently, collaboration requests sent to suppliers result in an update to the Supplier profile which will return in User Profile System search results. User Profile searches are functioning as intended based on Ariba “out of the box” search functionality. | DMS Requested | DMS
| CS0079286 | 2023-09-01 | Request to allow access the RFQ details for events | Reporting | 3rd-Party | AOD does not currently have functionality to run a report of RFQs and associated details of the event (terms, suppliers invited, supplier responses, supplier(s) awarded, etc.) administered within the system. There are not sufficient resources to include purchasing staff for every RFQ event conducted. An alternative mechanisms to review RFQs conducted within AOD is needed. | Agency Requested | DOH
| CS0073432 | 2023-07-17 | Add new Approver when PCard Flag is updated during requisition approval | Requisitions | MFMP-controlled | AOD does not currently have functionality to add a individual approver to a requistion approval flow when an individual field, such as the PCard Flag is edited during the requisition approval process. This enhancement will require SAP Ariba to customize the requistion approval edit rules to allow for the addition of an individual approver when the PCard Flag selection is updated on a requisition. | Agency Requested | DCF
| CS0073753 | 45126 | Request to edit message when using RFQ function in AOD | Sourcing | MFMP-controlled | The message "Please follow the guidance in the "How to Use This Contract" document on the DMS State Contracts and Agreements webpage to confirm you're inviting the appropriate number of vendors." needs to be added to the MFMP Supplier Touch Policy message when using the STC RFQ functionality in order to decrease confusion and ensure the appropriate number of vendors are invited to the RFQ event. | Agency Requested | DOH
| CS0086647 | 2023-11-13 | Request to send preparer notification when a PR is rejected/set back to Composing status due to ERP errors | Notification | 3rd-Party | PR215604-V2 was set back to Composing status due to ERP errors and the user who initiated the change order, Anansa Johnson (Contracts), did not receive a notification regarding rejection. Inorder to take the right actions, the preparer would like to be notified. | Agency Requested | DEP

## Open-S&C
CR # | Ticket # | Issue Open Date | Title | Functional Area | CR Type | Description | Business Driver | Agency Requested | Hour Estimate
| CS0073084 | 2023-07-13 | Interface for Import of Department Catalog File of CFDA and CSFA records for FACTs Contracts | Interfaces | MFMP-controlled | As part of the addition of MFMP Contracts facts integration functionality, DMS has requested new functionality to accommodate additional accounting details provided by DFS for FACTS Contracts. The scope of this enhancement will include the import of Departmental Catalog files for Federal Domestic Assistance (CFDA) AND State Financial Assistance (CSFA) in AOD. | DMS Requested | DMS
| CS0073753 | 45126 | Request to edit message when using RFQ function in AOD | Sourcing | MFMP-controlled | The message "Please follow the guidance in the "How to Use This Contract" document on the DMS State Contracts and Agreements webpage to confirm you're inviting the appropriate number of vendors." needs to be added to the MFMP Supplier Touch Policy message when using the STC RFQ functionality in order to decrease confusion and ensure the appropriate number of vendors are invited to the RFQ event. | Agency Requested | DOH

## Open-Next Gen VIP
CR # | Ticket # | Issue Open Date | Title | Functional Area | CR Type | Description | Business Driver | Agency Requested | Hour Estimate
| CS0013499 | 2022-04-21 15:16 | Update Vendor Advertisement Notification with 'Agency Advertisement Number' | VIP | MFMP-controlled | Request to include the Agency Advertisement Number in the advertisement notification Emailed to vendors. Currently, only the system-generated advertisement number is included within the notification. | Agency Requested | FDOT
| CS0012509 | 2022-04-12 13:19 | Update "My Advertisement" queue with 'Agency Advertisement Number' | VIP | MFMP-controlled | Currently, the 'Number' field within the My Advertisements section displays the system-generated advertisement number. This request is to update this value to display the 'Agency Advertisement Number'. | Agency Requested | FDC
| CS0011875 | 2022-04-06 14:51 | Update Advertisement Notification email notification for Closed Advertisements | VIP | MFMP-controlled | Currently, a dedicated email is sent when a VIP Advertisement is Opened or Updated and a separate email is sent when a VIP Advertisement is withdrawn. This request would add a dedicated notification email for the closing of VIP Advertisements. | Agency Requested | DCF
| CS0011383 | 2022-04-04 08:00 | Allow Attachment Sorting during Advertisement Edit. | VIP | MFMP-controlled | Currently, Advertisement Attachments are displayed in the order they are uploaded with no functionality to re-order the attachments during advertisement edit or when viewing the advertisement. This request would evaluate adding attachment sorting functionality. | DMS Requested | DMS
| CS0015614 | 2022-05-09 | Request to allow VIP to remember a device for Multi-factor Authentication purposes | VIP | MFMP-controlled | Currently admin accounts need to perform Multi-factor Authentication each time they log into the VIP application. This request is to allow the VIP application to remember a user's device for a certain amount of time so that they can bypass the MFA process when logging in. | Agency Requested | HSMV
| CS0020656 | 2022-06-30 | Request to increase max character length of the company website field within the vendor profile | VIP | MFMP-controlled | The current maximum character length that a vendor can input in their profile for their company website is 60 characters. This request is to increase the maximum character length in order to support longer URLs. | DMS Requested | DMS
| CS0040922 | 2022-11-02 | Request for newsfeed post to assist with advertisement search | VIP | MFMP-controlled | Known issue 3873 affects user navigation through multiple pages of search results within the VIP advertisement search. This request is to post a newsfeed on the public advertisement search page, which provides instructions for vendors on how to increase the Maximum Results criteria, how to export the search results to Excel, or provide other details that can assist vendors with identifying available advertisements. | Agency Requested | DCF
| CS0049127 | 2023-01-18 | Request to increase the character limit for the Contract Number -> Other Number field to 50 chars | VIP | MFMP-controlled | When submitting a report in VIP for a vendor, upon selecting 'Other' for the Contract Number, a free text field is then used to input the contract number. The current limit for this field is 25 characters. To assist with BCS purposes, this request is to increase this field to a max of 50 chars. | DMS Requested | DMS
| CS0049225 | 2023-01-19 | Request to display a count of vendors for each minority designation within the VIP public view | VIP | MFMP-controlled | This request is to display a count of vendors who hold each type of minority designation. This count will be displayed on the public facing VIP page. | DMS Requested | DMS
| CS0054256 | 2023-02-24 | Request to omit vendors on the Court Reporting Services 82111603-19-01 State Term Contract from receiving a QSR Past Due notification | VIP | MFMP-controlled | Vendors on the Court Reporting Services 82111603-19-01 State Term Contract are not required to submit a Quarterly Sales Report. As a result, they should not receive any past due notifications that are generated by VIP. | DMS Requested | DMS
| CS0061689 | 2023-04-20 | Request to map Publish time on AOD Sourcing Event to Start Date/Time on VIP Advertisement | VIP | MFMP-controlled | This request is to update the mapping between an AOD sourcing event and the corresponding VIP advertisement. Currently, the "Start Date/Time" on an integrated advertisement in VIP is populated with the "Planned response start date" in the AOD sourcing event. The request is to update this mapping so the the "Start Date/Time" is populated with the "Publish time" from the AOD sourcing event. The "Publish time" is already used to populate the "Published Date/Time" on the VIP advertisement. The result would be that the "Published Date/Time" and "Start Date/Time" would display the same value for an integrated advertisement. | DMS Requested | DMS
| CS0066685 | 2023-05-26 | Request to add Unique Entity ID (UEI/SAM) and 4-digit zip code on vendor registrations | VIP | MFMP-controlled | The Department of Transportation is requesting a VIP enhancement to add fields for an optional 12-digit Unique Entity ID (UEI/SAM) and 4-digit zip code in a vendor's registration. Vendors will be able to input this field within the 'Business Profile' page when registering. This information will show in the 'General Vendor Information' once registration is complete. Additionally, this request will update existing VIP reports and Tableau dashboards to include the new fields. | Agency Requested | DOT
| CS0075705 | 2023-08-02 | QSR Template Redesign | VIP | MFMP-controlled | The Department of Management Services has requested revisions to the Excel Template used for Quarterly Sales Report (QSR) submissions in VIP. The proposed revisions are intended to improve the data captured in VIP for QSR submissions. | DMS Requested | DMS
| CS0075820 | 2023-08-03 | Update to AOD to VIP Integration for Agency Decision Advertisement Creation | VIP | MFMP-controlled | Update to AOD to VIP Integration for Agency Decision advertisement creation to accommodate updates to the VIP Decision Advertisement Description folder name. | DMS Requested | DMS
| CS0075826 | 2023-08-03 | Sort Advertisement Attachments Table by Create Date/Time in VIP | VIP | MFMP-controlled | Currently, Advertisement Attachments are displayed in an unsorted order. This request would evaluate updating advertisement attachment list to be sorted by attachment name or modified date. | DMS Requested | DMS
| CS0076286 | 2023-08-08 | Request to update AOD to VIP Integration for Integrated Advertisements to no longer refresh "Date/Time" for un-edited Event Attachments. | VIP | MFMP-controlled | Currently, Sourcing Event edits refresh all VIP Advertisement details, including attachments. For example, an edit to the event content will initiate AOD > VIP event integration. AOD VIP Integration will result in the "Last Modified Date" for attachments to be set to the current date. Request to explore new system functionality to perform a checksum of old vs existing attachments and only update changed attachments. Keep prior date for unchanged attachments. | DMS Requested | DMS
| CS0081221 | 2023-09-19 | VIP Advanced Search Status Filter Enhancements | VIP | MFMP-controlled | Currently, VIP advanced search functionality in both public and admin vendor searches allows the filtering of search results by vendor status and vendor location status. By default, no vendor or location status filters are selected and advanced searches using the default status filter selections will return results including active and inactive vendors and locations. Current search functionality allows advanced searches to be submitted with both active and inactive vendor status and location status filters selected and will return the same results as a system search with no vendor status or location status filters selected. This request would evaluate updates to the system search functionality to ensure status-based searches behave in a consistent manner. | DMS Requested | DMS
| CS0083772 | 2023-10-12 | Request to add a password reset functionality in VIP | VIP | MFMP-controlled | Currently, when a user has multiple VIP accounts with the same email address, they receive a popup message to contact the Customer Service Desk (CSD). Rather than VIP directing customers to the CSD, I would like us to enhance the reset functionality to instead present the user with options of which accounts they have, and allow them to select which account they're attempting to reset their password for. | DMS Requested | DMS
| CS0086307 | 2023-10-08 | Modify Calculation and Assignment of End Date/Time for Integrated Agency Decision Advertisements | VIP | MFMP-controlled | When a sourcing event has received at least one vendor response and moves to Completed status, the process is initiated to create an agency decision advertisement in VIP via the Advertisement Award task. This advertisement is created with the Start Date/Time of the Advertisement Award task and the End Date/Time is calculated based on the Start Date/Time. Updates to the integrated agency decision advertisement creation process are recommended to align with Florida statute and account for weekends and state holidays. | DMS Requested | DMS

## Open-Tableau
CR # | Ticket # | Issue Open Date | Title | Functional Area | CR Type | Description | Business Driver | Agency Requested | Hour Estimate
| CS0039107 | 2022-10-18 | Request to add legacy State Address ID data into Next Gen MFMP | Reporting | MFMP-controlled | As part of the migration from the legacy MFMP application to Next Gen MFMP, the 'Address ID' and 'State Address ID' values have been consolidated into a single field. This request is to add the data from the legacy State Address ID field into Next Gen MFMP to assist with System Administrator duties. | Agency Requested | DOH
| CS0039009 | 2022-10-17 | Update the PO, Invoice, and FLAIR Tableau dashboards to include Minority-Business Designations | Reporting | MFMP-controlled | This request is to include the Minority-Business Designations for a vendor within the PO, Invoice, and FLAIR Tableau dashboards. This will include the MBE code and associated description. Non-Certified Minority-Business Designations will be included within this request (ex. N - African-American, Non-Certified). | DMS Requested | DMS

## Approved
CR # | Ticket # | Issue Open Date | Title | Functional Area | CR Type | Description | Business Driver | Agency Requested | Hour Estimate
NG.VIP.005 | CS0056807 | 2023-03-15 | OSD Certification Template Revision | VIP | MFMP-controlled | As part of the MyFloridaMarketPlace (MFMP) Cloud Transformation, administrators from the Department of Management Services (DMS) Office of Supplier Diversity (OSD) are required to review certification and recertification submissions for vendors seeking a Certified Business Enterprise (CBE) designation in the MFMP Vendor Information Portal (VIP). As a result, certificate documents listing vendor designations must be generated by VIP using a template provided by DMS OSD. Certificates generated by VIP must be made available for download by certified vendors. Certificates generated by VIP reference Florida Statutes, DMS secretary details, OSD branding, and contact information are subject to change. Currently, updates to the OSD certificate template can only be accomplished by changes to the VIP application code. This enhancement aims to decouple the OSD certificate template from the VIP application code. As a result of this change, updates to the certificate template will be managed as part of the existing SLE-15 Operational Data update process and no longer require a VIP code release or hotfix. | DMS Requested | DMS | 193
NG.VIP.006 | CS0013215 | 2022-04-19 | OSD Enhancement Package | VIP | MFMP-controlled | The Office of Supplier Diversity (OSD) has requested updates to the OSD functional area in the MyFloridaMarketPlace (MFMP) Vendor Information Portal (VIP) to support the evolution of their business processes. To facilitate these changes, VIP will be updated to give OSD admin users access to view, populate, and edit fields previously only available to vendors as part of the certification or recertification application. In addition to other quality of life enhancements, OSD will have greater flexibility when managing vendor CBE profiles. To support OSD business processes, VIP will be updated to allow OSD admins to granting certifications or revoke certifications on an ad hoc basis. The OSD Admin Search page will be updated to allow for more specific and targeted searches, accommodating OSD’s quality assurance process. The VIP updates outlined in this enhancement include the changes previously requested via CS0038812 - Request to display Non-Certified Minority-Business Designations on vendor profiles | DMS Requested | DMS | 798

## Closed
CR # | Ticket # | Issue Open Date | Title | Functional Area | CR Type | Description | Business Driver | Agency Requested | Total Hours Assessed
NG.AOD.001 | N/A | 2021-12-01 | AOD Buying & Invoicing Custom Field Bundle | Buying & Invoicing | 3rd-Party | AOD Buying & Invoicing Custom Field Bundle | DMS Requested | DMS | 106
NG.VIP.004 | CS0035506 | 2022-09-20 | Request to Update Address in VIP for Transaction Fee Payments | VIP | MFMP-controlled | Request to update the address for vendor payments where it is displayed in VIP. This information is shown on the Transaction Fee Payment Methods tab of the Billing and Collections section for a vendor. | DMS Requested | DMS | 36