## Open
ID | Title | Functional Area | Description | Comments | Hour Estimate | Votes
Legend:
2 | Vendor 'Remit To' address,'Does Business As' name and 1099 name on invoice and printed PO | Ariba Buyer | Vendor 'Remit To' address,'Does Business As' name and 1099 name on invoice and printed PO. |  | 484 | 2 - DCF, FWC
22 | Data scoping | Ariba Buyer | DMS has requested that system searches and standard reports be scoped by entity. This will prevent agencies from returning search results containing other agencies transactions. By limiting access to agency’s transactions, it will limit access to attachments.
26 | Mass Edit IRs | Ariba Buyer | Changes will be made so that users can mass edit accounting fields on the line items of IRs. The following a defined as accounting fields for the purposes of mass editing (these are the accounting fields currently available for editing on an individual line item): organization code, prefix, expansion option, object code, budget entity, int budget indicator, category, category year, state program standard, external program, grant, other cost accumulator, contract, agency unique, contract year, grant year, project id, ext category, general ledger, ext general ledger, product id, ext object, grouping character, BPIN, certified forward indicator, batch, description, quantity, count, transaction fee exempt, transaction fee exempt reason, sub-vendor, times and units. | Deferred | 1116 | 10 - AHCA, DC, DCA, DEP, DJJ, DMS, DOH, DOR, DOT, HSMV
29 | Include Voucher # and SWDN on payment update eForm | Ariba Buyer | Add the ability to update the Voucher # and Statewide Document # on the Company eForm for Payment Update so those invoices that have been processed directly through FLAIR (marked as "Paid in FLAIR") will have all of the same information as the other payments made in MFMP. |  | 50 | 3 - DCF, DEP, DOH
30 | Contract id on DO to vendor | Ariba Buyer | The order generated by MFMP that is transmitted to the vendor does not include the contract number. Some vendors are on multiple state contracts, or have multiple agency contracts, or a combination of both. The lack of the contract number on the order creates confusion for some contractor's billing offices, and they have contacted our agency on multiple occasions to ask which contract the purchase applies to. The online request and order both only display the contract number, but for some reason the vendor's copy does not. The vendor's copy will display "State Contract" or "Agency Contract". |  | 40 | 2 - DCF, DMS
31 | Approval in progress indicator on Invoice Reconciliation & Requisition | Ariba Buyer | Users have requested the ability to be able to determine when a Requisition or Invoice Reconciliation (IR) is being worked on by another approver. Add an “Approval in Progress” checkbox to the header of the Requisitions and IRs. This new field will be used to indicate that a certain Requisition or IR is being worked by another user. Users will have to edit the approvable to set the indicator manually. In addition, this indicator will be displayed in the Approve Request queue for requisitions and displayed in the Reconcile Invoice queue for IRs.
34 | Add six-digit commodity code to Sourcing | Sourcing | Sourcing 2.0 will be modified to accommodate six-digit commodity codes (first three digits designate class and next three digits designate group). Customers would like to have the option to select the entire class and/or drill down within the class to select specific groups. In addition, customers would like to continue to have the ability to drill down even further and select specific suppliers within a group. Customers would like the commodity codes to include descriptions and the suppliers to be listed alphabetically by supplier/company name.
35 | Edit capabilities on Master Agreement Requests | Contracts | Changes will be made to the edit functionality for MARs to allow users to edit the following line item fields when changing a MAR: “Full Description”, “Unit of Measure”, “Supplier Part Number” and “Commodity Code.” Changes will also be made so users can edit the “Release Required” field when changing a MAR. Changes will be made to allow users to delete existing line items when changing a MAR. Changes will also be made to copy comments from a MAR to the associated MA once the MAR is fully approved. |  | 404 | 2 - DMS, DOT
38 | Redesign PUR 3776 eForm | Billing & Collections | Change layout of report submittal page. (Dynamic transaction fee entry)
41 | CFO Received Date | Ariba Buyer | There is an issue with prompt payment reporting. At the present time, when DFS calculates an agency’s prompt payment they don’t have particular fields available to them from FLAIR (i.e., the date that the Invoice Reconciliation (IR) is received by the auditor). Instead, they are utilizing a date that is captured after the auditors have approved the transaction for payment. This causes the prompt payment report to include the agency’s processing time and the auditor’s processing time as a part of the agencies 20 day time frame.
42 | Add accounting detail to Analysis | Reporting | We would like to have searchable accounting data fields added in Analysis. Finance and Accounting need analysis reports to utilize fields such as object code, organization code and the category that PR and Invoices are coded in order to track spending history and to accurately track the agency’s budget allotments. | Open | 496 | 4 - DEP, DJJ, DMS, HSMV
48 | Service Start/End Date loaded into Buyer from ASN invoices | Ariba Buyer | When a user enters an Invoice Eform for a leased item, there are two dates that can be entered that assists the invoice approver in determining the validity of the invoice, Service Start Date and Service End Date. To successfully load an electronic invoice that requires this information, a change must be made to map the extrinsic values ServiceStartDate and SerivceEndDate in Ariba.
49 | SPURS sunset - phase 2 | Vendor Registration | Phase 2 of SPURS sunset (W-9 Request for TIN)
54 | Redesign of VMS registration instructions | Vendor Registration | Remove long instructions paragraphs on login and reporting pages as they make some pages unnecessarily long, or at least move them to a different location (e.g., link to new browser session).
55 | Display specific error messages on Report Submission Page | Billing & Collections | Enable error-specific messages on the Report Submission page instead of one all-purpose 'blanket' error (historical CR 284). The Department of Management Services has requested that error specific messages display on the report submission page rather than the 4 generic messages that currently display. They have also requested that the exact location of the error on the report submission page be highlighted or identified to inform the vendor of where the problem is occurring.
56 | VRS Self Search Sequence and PIN | Vendor Registration | Create searchable database on vendor section of the website…’click here to request your sequence and PIN number’
57 | Confirm VRS Main Contact Email | Vendor Registration | Confirm the email address entered on main contact of registration is valid as part of registration process.
59 | Add additional solicitation indicator to VBS/Spurs Interface | Vendor Registration | To allow the automated registration in VBS for vendors that have indicated on their MyFloridaMarketPlace Vendor Registration that they are interested in being notified of any solicitations. The information provided through the current nightly interface for use within SPURS, does not contain this additional information. Without this additional information, the vendor will continue to be asked to register within the VBS tool as a separate part of being notified of solicitations that occur outside the MyFloridaMarketPlace suite of applications.
199315 | Show zip code on "Choose Value for Ship To" screen | Ariba Buyer | Currently, the following fields are displayed on the "Choose Value for Ship To" screen: ID, Name, Entity, State Address ID, Street, City, State, Country. We would like to see the zip codes displayed on this screen as well The "Country" is always "United States" and really is not necessary in this view. When performing System Administrator duties, viewing the entire address would eliminate the need to open each record to see the zip code.
199889 | Add authorized agent who approved the PO to the PO | Ariba Buyer | Rule 60A-1.016(2) Florida Administrative Code, requires "the purchase order shall be signed by the authorized purchasing or contracting personnel." Section 668.003(4) Florida Statutes allows an electronic signature consisting of "any letters, characters, or symbol, manifested by electronic or similar means, executed or adopted by a party with an intent to authenticate a writing." Therefore, the authorized agent's name should be reproduced on the purchase order.
213080 | Restrict Contract Release Access by Entity AND PUI | Ariba Buyer | Customers want the ability to restrict release access on a contract purchase by Entity AND PUI. Currently, the module is set up only for restriction by Entity.
213111 | Add New Category to Contract Type in the Contracts Module | Ariba Buyer | Add Substance Abuse Program as a Consulting/Service option to the Contract Type dropdown field. This is a valid choice that is not being displayed in this field.
213112 | Default 'Include Comments/Attachment(s) on Purchase Orders' checkbox as unchecked | Ariba Buyer | The 'Include Comments/Attachment(s) on Purchase Orders' checkbox should be defaulted to unchecked. This change request includes comments added as a result of FLAIR integration. |  |  | 3 - AHCA, HSMV, FWC
213116 | Update Vendor Navigation Toolbar link update | Billing & Collections | Customers have requested that the `View CBI` and `Submit Transaction Report` links on the Navigation Toolbar within VRS be consolidated into one link since both links take the vendor to the Bill-To contact selection page. The new link should be titled `Transaction Fee Report Submission`.
213119 | Sum the Total fields on the Report Interview Continued | Billing & Collections | Customers have requested that the table on the Report Interview Continued page be updated to sum the columns in the Total field rather than requiring the vendor to total the fields . This would apply to STC/SPA vendors only.
213120 | User Eform Summary | Ariba Buyer | When adding a user, the customer would like the User Eform Summary to display the Name of the Bill To and Ship To addresses instead of the system generated letter/number combination that doesn't relay any valuable information to the system administrator. |  |  | 1 - AHCA
213129 | New form of Contract for State Purchasing Agreement | Contracts | Customers have requested that State Purchasing Agreement (SPA) be added to the Form of Contract drop down box. This will allow customers to keep STC Master Agreements and SPA Master Agreements separate. Currently there is not a flag in MFMP to distinguish a Master Agreement as a SPA. This will also be very beneficial for reporting.
213130 | Fiscal year added to system searches | Ariba Buyer | When using the search function and selecting a time frame, one of the options should be fiscal year. We are always doing reporting of some kind and if this drop box included that function it would be much easier for agency because we report on fiscal year not calendar year. It would save a lot of time in the long run and allow us to be more efficient.
213131 | BCS - Ariba Contracts Interface | Billing & Collections | Need an additional interface to Ariba that will supply the BCS with a list of STC/SPA contacts and the FEIN/Location associated to each as well as the start and expiration dates for each contract. This will also require a modification to the UI - will need to remove some logic that populates the form from the MFMP table and have it populate the STC and SPA numbers off of the new contract information provided by Ariba Buyer. This will also require at least one more additional table to the BCS data model.
213133 | Suspended vendors shouldn't have the ability to re-register online | Vendor Registration | Currently, if a vendor record is in the status of "suspended" the vendor can go to the online vendor registration system and re-register using the same tax id and company name or the same tax id and different company name. If a vendor types in a tax id a query should run to check and see if a vendor record exists and the status of the vendor record. If the query returns a vendor record and a status of "suspended" the application should lock out the vendor from registering and post the below message: "This vendor was suspended on XX/XX/XXXX and is not allowed to re-register online. Please contact XXXXXXXX at XXX-XXX-XXXX or at XXX@XXX.com for further information".
213211 | VRS not requiring bill to email address | Billing & Collections | Currently the vendor registration system does not require vendors to have a bill to email address. This causes problems for the billing and collection system as it relates to communicating vendors.
222243 | Add message to Vendor Reg screen | Vendor Registration | Add the following message to the vendor registration screen: Two business days following your registration you can sign up for automatic email notification of bids. Go to http://fcn.state.fl.us/owa_vbs/owa/vbs_www.notification_new.selection Enter the requested information under “Add Email Notification” and you will then be signed up to receive notification of bids for any of the commodities/services for which your business is registered.
244431 | Radio Button for Archive folders | Ariba Buyer | Currently the system only allows you to move one folder at a time for archiving items because the radio button only allows one at a time. During the process of moving all folders used for current year in MFMP to a parent folder called 2005-2006, it is only possible to move one folder at a time. It would be wonderful if it was possible to move all 20 folders at one time instead of having to use the radio button which only allows one folder at a time to be moved.
245628 | Workflow regeneration from Need-by-Date | Ariba Buyer | When a MFMP user who has “CO No Workflow” role goes into the requisition to make accounting changes, the “need-by-date” must be changed (if that date has passed). This in turn adds workflow to the requisition. Changing an object code or taking a “C” out of the certified field, etc. should not cause workflow. The item(s), most likely were received by the need by date, the dollar amounts did not change, and the approver has already approved the purchase once. Change the system so that the “need-by-date” doesn’t trigger workflow when making changes that fall under the “CO no workflow” criteria. Need-by-dates are information for the vendor and do not effect the item purchased, the dollar amount of the item, or the fact that the approver has already approved the purchase. |  |  | 1 - DOR
260014 | Recycled and Green Reporting | Ariba Buyer | The department shall design a uniform reporting mechanism and prepare annual summaries of statewide purchases delineating those with recycled content to be submitted to the Governor, the President of the Senate, and the Speaker of the House of Representatives. DMS has a duty as provided in 287.045(11) to provide a recycling report to the Governor and the legislature; DMS can capture a fraction of the recycling information via MFMP and SPURS; MFMP can be augmented to permit state purchasing to capture more recycling information that DMS can currently capture Include a “recycled indicator” checkbox that can be manually edited on the purchase requisition for each line item. Information will need to be included in Analysis within the data field of “Recycled Materials”. This indicator box is to be used by agencies when the product they are ordering is a non-catalog item that is recycled, or is a catalog item but is not appropriately loaded as a recycled product and the selection of recycled needs to be made. At the request of an agency on 9/30/2008, the original change request is being amended to include the ability to select and capture spend on non-catalog “green” products in MFMP through the use of a checkbox that will be manually edited on the purchase requisition. Therefore this change request will be to add an editable indicator field for “recycled” and for “green” products. The initiative to select and be able to report on “green” products is only capable through the use of catalog line items. We are requesting that MFMP be augmented to allow State Purchasing and the agencies to capture more green product spend than DMS can currently capture. |  |  | 1 - DOR
260923 | CO No Workflow Changes | Ariba Buyer | CO No Workflow Role allows editing of 53 fields including procurement and accounting information without workflow regeneration. We would like a new role established (ACCT CO No Workflow) that will allow editing only of the 38 fields used by accounting (see attached) so that no purchasing information can be edited by accounting staff. Edits to any of the 38 fields are allowed without workflow regeneration. Editing of the 15 purchasing-related fields will not be allowed. |  |  | 1 - DC
266017 | Printing Budget Category on PO | Ariba Buyer | The requisition is printed during the approval process in order to review for accounting accuracy. Certain accounting information prints such as the organization code, object code, and expansion option. There is one vital piece of information that is omitted from the printed document and the screen when in print mode and that is the budget category. Customers would like to have the budget category displayed along with the other accounting information that is displayed on the screen when in print mode or when the requisition is printed.
272573 | Add Management Levels | Ariba Buyer | Customers request that the Management Level table be revised to include one additional dollar levels. Some managers have a delegated authority of $350,000. This level does not appear on the current Management Level table. Customers have requested the following management levels be added: • $250 • $1,500 • $30,000 • $1,000,000 • $5,000,000 • $10,000,000
272661 | IR Search by Master Agreement | Ariba Buyer | Allow users to search for a “complete” payment history of Invoice Reconciliations (IR’s) using a Master Agreement number that will show “ALL” payments made under that root Master Agreement number regardless of new versions. Example: System Searches / Invoice Reconciliations / Order ID: MA15691 / PUI of Requester: 5505 When you perform the above search for Invoice Reconciliations on Order ID: MA15691 (no version number), you only receive a list of IR’s that have been paid under the “new version” V5 since 03/17/07. It does not show the previous 12 invoices paid since the beginning of MA15691 that totals $17,302.15. *We would like this search to result in all IR’s paid under MA15691. | MFMP will clarify the intent of this change request (determine if CR 3 satisfies this request). 1/29/08 Update: MFMP still seeking clarification from DOT on the intent of this change request
274916 | Commodity code printed on the requisition | Ariba Buyer | Currently, commodity codes can only be obtained by logging onto Ariba and researching the requisition to see what commodity codes were used for various purchases. Also, for shipping and handling we are using commodity codes and object codes that really do not correspond with this particular charge. This is a charge that is used frequently. We would like to have the commodity code printed out onto the requisition to enable staff to research commodity codes used with various purchases. There should be a commodity code and an object code for shipping and handling. We are using the commodity for envelop/shipping and for freight as an object code. Shipping and handling should have its own code.
285996 | MFMP error messages due to FLAIR integration on print | Ariba Buyer | MFMP error messages due to FLAIR integration are printed on the Purchase Order. These messages are unnecessary and confuse the vendor; they add unnecessarily to the length of the order |  |  | 3 - AHCA, DC, DJJ
286593 | Flag IRs rejected by DFS | Ariba Buyer | Invoice Reconciliations that are returned to the agency by DFS are not easily identified. This causes workload management issues and potential prompt payment issues, as user’s cannot identify work that needs immediate attention. |  |  | 3 - DCA, DOR, FWC
288255 | Start date/End date | Ariba Buyer | When creating a requisition there is no validation on the PO start and end date fields; a PO start date can be after the end date. | MFMP will confirm whether or not these fields are customized.
290914 | When copying p-card requisition, do not copy p-card number | Ariba Buyer | When a user copies a requisition from another user that used their p-card number in the requisition, the copied requisition will not only copy the line information but also copy the p-card number. This is a security violation and the copy feature needs to be addressed so as when it is used, no p-card information is copied. | MFMP will confirm this issue in the training environment.
294097 | Remove supervisor approval for delegation | Ariba Buyer | Delegations currently must be approved by the supervisor. The approvals should be handled by the designated delegate and follow the already approved workflows in the system. |  |  | 1 - DOT
294204 | Add county code to vendor load in MFMP | Reporting | At this time, the county code information is not populated in the Buyer application. Florida vendors are required to enter their county information when completing a Vendor Registration account, but this information does not populate to the vendor’s file in Buyer and the County Code field does not exist. As a result, the county code is not search criteria that can be used to create a report.
296427 | Remove visibility of subvendor field on line item accounting | Ariba Buyer | When purchasing certain items (training courses, conference registrations, and travel related expenses) DFS requires that the benefiting employee’s social security number (SSN) be recorded in the sub-vendor field in FLAIR. If these procurements are issued through MFMP, then the SSN will need to be recorded in the sub-vendor field on the accounting details page of either the requisition or invoice reconciliation. | DMS will confirm the subvendor is still a requirement on disbursements for travel related expenses.
302020 | Add PUI to default DO search | Ariba Buyer | Searching by PUI is available in Search for Requisitions and Encumbered orders but not in the Search for Direct Orders function. Current process requires that user know the PR number in order to search by PUI. |  |  | 2 - DCA, DOT
307139 | Temporary password reset expiration | Ariba Buyer | Currently, Ariba Buyer has an infinite Time-To-Live (TTL) setting for its temporary passwords. DMS Policy dictates systems have an eight hour Time-To-Live (TTL) setting for temporary passwords. Ariba Buyer should be modified to meet the DMS Policy requirement.
310962 | Add fields to system search results (and increase result set count) | Ariba Buyer | Currently there are limitations to system searches: return results are limited and few fields are displayed (and therefore cannot be exported). The Operational Reporting Work Group would like to add fields to all system search results: Vendor name, Purchase Requisition #, Direct Order #, and Encumbrance #. These fields should always be displayed when searching for: Direct Orders, Purchase Requisitions, Contract Requests, Contracts, Invoice Reconciliations, Invoice eForms, Payments, Receipt, Delete Disbursement and Cancel Requisition.
321966 | Method of Procurement updates | Ariba Buyer | Some of the statutory (F.A.C.) references do not apply to some agencies (like the Department of Lottery). Their procurement authority is not delegated by DMS as set forth in Chapter 287 as it is for other state agencies. Their procurement authority is established in Chapter 24 and gives them any authority that DMS has under various chapters including 255 & 287 and any rules adopted there under. Previously when the method of procurement codes were "A=State Contract, E = PRIDE, RESPECT, Government, and G=Single Source", this was not an issue, as it was very general and broad in nature. Now that the purchasing methods are very specific to rule references, it results in incorrect purchasing method references for agencies like the Department of Lottery. The request is based upon business needs and concern over the inconsistencies resulting in unwarranted audit scrutiny causing an inefficient audit or payment process or a constant educational process of auditors on the differences. Additionally, the inconsistencies/inaccuracies is causing training issues (i.e. confusion of end users) when agencies provide general procurement and MFMP training to our Purchasing Liaisons and will necessitate increased scrutiny of MFMP transactions to ensure proper selection of the procurement method. This increased scrutiny will diminish any administrative efficiency gained through streamlining the workflow processes. The Department of Lottery is also requesting a Lottery specific “fee exemption” code that can be selected for procurements where the exemption provided in Rule 53ER07-55(10), Florida Administrative Code will apply.
336282 | Extend Buyer timeout to 30 minutes | Ariba Buyer | Currently, a user's session will be automatically logged out of Buyer if there is no activity for 15 minutes. Customer is requesting to extend the timeout period to 30 minutes.
339409 | Modify history to indicate PO was not sent to vendor when "Do Not Send to Vendor" is checked | Ariba Buyer | Currently, the history tab of a PO and requisition display a message that the DO was successfully sent to the vendor when the "Do Not Send To Vendor" checkbox is checked. This enhancement would change the message displayed in the history so that it is more accurate.
340090 | Default the "Do Not Send To Vendor" checkbox to checked on a pcard requisitions | Ariba Buyer | The current process requires the Purchasing Office to check the “Do Not Send To Vendor” box located on the first portion of a pcard requisition process prior to approving. This enhancement would default the "Do Not Send To Vendor" to checked upon a submittal of a pcard requisition.
340601 | Add contract number to encumbrance and disbursement requests sent to FLAIR from MFMP | Ariba Buyer | Agencies who desire to track spend by contract cannot encumber through MFMP because the contract number is not recorded in FLAIR. The Contract field is available on the accounting details page of an MFMP requisitions/IR however the contract number is not sent to FLAIR. This enhancement would allow the contract field to be sent to FLAIR when specified on an encumbrance or disbursement request (this contract field would then be subject to existing edits in FLAIR).
342637 | Update attachment functionality to allow multiple attachments to be added at one time | Ariba Buyer | The current process in adding attachments in the MFMP system is one at a time. This enhancement would allow users to add multiple attachments at one time.
348706 | Update MOP code "F" to read "informally quoted purchases $2,500 to $25,000 per Rule 60A-1.002 (3)" | Ariba Buyer | Update MOP code "F" to read "informally quoted purchases $2,500 to $25,000 per Rule 60A-1.002 (3)". The description for MOP "F" currently reads "informally quoted purchases not exceeding $25,000 per Rule 60A-1.002 (3)."
349694 | Update MOP code "E" to read "discretionary purchase $2,500 to $25,000 per Rule 60A-1.002 (3)" | Ariba Buyer | Update MOP code "E" to read "discretionary purchase $2,500 to $25,000 per Rule 60A-1.002 (3)". The description for MOP "E" currently reads "discretionary purchase under $2,500 per rule 60A-1.002 (3)."
349820 | Allow users to edit their e-mail notification preferences for Requisition Withdrawals | Ariba Buyer | This change would allow users to modify their email notifications for withdrawn requisitions (currently, it is not possible to disable notifications sent when a requisition is withdrawn).
349821 | Updates to the PO Amount Ranges in Analysis | Reporting | This change would allow users to create reports in Analysis that are consistent with the thresholds specified in the Florida Statutes and the Florida Administrative Code.
354816 | Old attachments transmitted to vendors on change orders | Ariba Buyer | Currently, when a change order is approved and submitted to the vendor, all attachments are included (including those attachments on previous versions of the order). With this request, if a change order does not include an attachment then the original attachments would not be transmitted to the vendor. However, if a change order involves a new attachment, only that attachment would be sent to the vendor.
357929 | eForm to restore encumbrances for cancelled or failed warrants | Ariba Buyer | If a warrant is cancelled or an encumbered disbursement fails Central FLAIR, the encumbrance is reduced in FLAIR but there is no way through MFMP to restore the funds. The causes agencies to create new encumbrances directly in FLAIR and perpetuates the discrepancies between MFMP and FLAIR. MFMP needs a way to restore funds to an encumbrances line when a warrant is cancelled or a transactions fails Central FLAIR (perhaps via an eForm).
358430 | Add logic to require contract based on the selected MOP selected on requisition line item | Ariba Buyer | Currently, when a non-catalog requisition is completed and the Method of Procurement is selected as an A or B, there is no mandatory requirement to enter the appropriate STC#. There are no options to enter the ACS # or SPA# if the Method of Procurement of C or D is selected. Also, there are no options to enter an Agency ITB#, Agency RFP# or Agency ITN# if the method of Procurements of H, H1, I, I1, J, J1 are selected. With this change request, a State Term Contract #, ACS#, SPA#, ITB#, RFP# or ITN# would be required when entering one of the following Method of Procurement on a requisition: “A”, “B”, “C”, “D”, “H”, “H1”, “I”, “I1”, “J”, “J1”
363916 | MA link on IRs for MAs with and without release required | Ariba Buyer | On the IR, the MA link should appear with or without the requirements of a release. The functionality should be the same as the MA without release as described below. When an IR is created against a Master Agreement (MA), unless the MA is a contract without a release, the MA link cannot be selected on the IR whereby it takes you directly to the MA information and the MAR link. Those steps are as follows: MA without release: IR has the contract field populated (and linked) Click on the link and it takes you to the: Review Details for Contract page Click on the link of the MAR and it takes you to the MAR to review When an IR is created against a Master Agreement (MA) that requires a release, the steps to follow to get to the MA/MAR is as follows: MA with release: IR does not list the MA# on the contract field nor does the Order ID field have links To get to the MAR, you have to: Click on the Orders tab Click on the Order ID (MA#) Scroll to the line items Find the MA# there (under the commodity code) and click on that link This takes you to the Review Details for Master Agreement page Click on the link of the MAR and it takes you to the MAR for review This creates a significant impact not only to the agency customer when they are reviewing the details of the order, but also to the Tallahassee auditors when they are reviewing the documentation that allows the purchase hence the payment against the procurement.
366273 | Modify process used for vendor search on Invoice eForm | Ariba Buyer | Currently, when an Invoice eForm is created, the Accountant must use the system search to find the FEID number tied to the Purchase Requisition/Direct Order for the Invoice(s) they are processing. This is usually then written down (probably on the invoice or copy of the DO) for each one. Once the searches are done and the FEID numbers are obtained, the Invoice eForms are completed. The Supplier information is selected based on the search the Accountant did to find the correct FEID tied to the Direct Order. Once this enhancement is implemented, the Invoice eForm will require entry of the “Purchase Order” , then from that the “Supplier/Vendor Location” fields would populate (or be pulled in automatically) depending on the information already tied to the Direct Order. This would make completion of the eForm more efficient and less time consuming.
366594 | Enable mobile version of MFMP 2.0 | Ariba Buyer | Agencies are requesting that MFMP 2.0 be accessible via mobile devices (such as Palm Treo Smartphones) so that users can complete approvals remotely.
376381 | Search for contracts by MOP | Ariba Buyer
53 | Password reset for Ariba Buyer | Ariba Buyer | Currently if a buyer forgets his or her MFMP password, the agency system administrator must reset the password. Agencies are requesting the ability for a buyer to reset his or her password without contacting the agency system administrator. The functionality would be similar to the vendor password reset enhancement.
380578 | Add ability to create new central receivers without ODU | Ariba Buyer
388002 | Vendors submit reports by state agency and OEU | Billing & Collections | State Purchasing requests that vendors be able to report fees by State Agency and Other Eligible Users. This will assist SP in ensuring that STC vendors are fully reporting their transaction fees.
388237 | Currently, there are Buyer Codes that need to be added for DFS’ procurement processes and additional information in the T’s & C’s that DFS would like modified | Ariba Buyer
397840 | MAR notification change OBO State Purchasing | Ariba Buyer | Currently when there is a MAR for a State Term Contract to approve, an email notification is sent out to all users in State Purchasing. Even if it is not their MAR. The change would prevent all of State Purchasing from receiving an email notification when there is a MAR to approve, only the individual responsible for the MAR approval.
400532 | Modify "Approved IR" email for rejected IRs | Ariba Buyer | Current system functionality produces an "Approved IR" email to requestors when an agency's F&A group approves or rejects an IR. Agency staff experience confusion when the "Approved IR" email is sent to the requestor for rejected IRs. Understanding that "approved" email is signifying the rejection is approved, generating an approval email for a rejected IR is incorrect and serves no purpose and provides conflicting information. Although our agency submits emails to requestors providing descrptive information on any rejected IR, the system generated "Approved IR" email is counterproductive.
TBD | Create a No Sales to Report button | Billing & Collections | Create a button that allow STC/SPA Vendors to automatically submit a zero sales report. Allow them to not populate their CBI Details page (STCs) May correspond with Item #19 CR 330.
Note on D40: AR:Should the #350,000 be added into the table?
Buyer CR - prioritized 1/31/08, not top 5
Buyer CR - unprioritized
Sourcing CR
Vendor CR
Buyer CR - prioritized 7/8/08 - TOP 5

## Approved
Master Ticket # or CR # | Title | Functional Area | Description | Comments
40 | IR Accounting Validation | Ariba Buyer | Currently if you are rejecting an IR, all the accounting must be validated in order to process the IR and get it in Rejected status. Additionally, if you are disputing a line item, you also must validate the accounting before continuing. This creates additional work and time to a simple process. 1. When rejecting an IR, do not require that the accounting be validated. 2. When disputing a line item, do not require that the accounting be validated. | In progress
60 | VRS user interface updates | Vendor Registration | VRS user interface (UI) updates to CSS (cascading style sheets) to change global fonts and colors for page elements
61 | Auto calculate total values when reporting for a STC vendor in BCS | Billing & Collections | The Department of Management Services has requested that the table on the Report Interview Continued page be updated to sum columns in the Total field rather than requiring the vendor to total the fields. This would apply to STC/SPA vendors only.
61 | Auto Populate STC/SPA number on the report | Billing & Collections | Allows for the dropdown selection of a vendor's STC/SPA number on the Transaction Fee Report in BCS that is completed by the vendor each month.
62 | Prepopulate charges values when reporting in BCS for non-STC/SPA vendors | Billing & Collections | The Department of Management Services has requested that the Transaction Fee Report for non-STC vendors be pre-populated based upon the transactions completed in MyFloridaMarketPlace for the prior month. Each field would be editable on the table. This change would not apply to STC/SPA vendors.
62 | Pre-populate the Transaction Fee Report for Non-STC vendors | Billing & Collections | The Department of Management Services has requested that the Transaction Fee Report for non-STC vendors be pre-populated based upon the transactions completed in MyFloridaMarketPlace for the prior month. Each field would be editable on the table. This change would not apply to STC/SPA vendors..
63 | BCS CBI History Page line extension | Billing & Collections | Review number of lines returned on CBI History Page (currently 50)
64 | Print Friendly button in BCS | Billing & Collections | Addition of a "print friendly" button (pop-up window that pre-formats page for printing) to allow vendors and BCS administrators to print VFTR
65 | Remarks field in BCS for administrators on payment submission page | Billing & Collections | Addition of a free text remarks field for use by BCS administrators on the payment submission page
66 | Vendor Payment History Access (Comptroller's site) from BCS | Billing & Collections | Have a button (or link) that vendors can click that links them to FLAIR to show their total payments for the month
66 | Vendor Payment History Access (Comptroller's site) | Billing & Collections | Have a button that vendors can click that links them to FLAIR to show total payment history.
67 | Commodity code search functionality for vendors in VRS | Vendor Registration | The Department of Management Services would like there to be full search capability when trying to locate the appropriate commodity code.
68 | Payment Address visibility / location in BCS | Billing & Collections | Display vendor payment address more obvious in location presented. Right now it is on the transaction fee report submission page.
69 | Default Payment page to Check By Mail in BCS | Billing & Collections | Change default on Payment page; currently defaults to EFT Debit Payment but should default to Check by Mail
70 | Reveal Audit Information on Payment Details in BCS | Billing & Collections | Confirm Audit Records and Display on Payment Edit pages

## Closed
Master Ticket # or CR # | Title | Functional Area | Description | Comments | Date Implemented | Action
213086 | Ad-Hoc reporting for Billing & Collections System | Billing & Collections | In order to support ad-hoc reporting for the Billing & Collections system, the MyFloridaMarketPlace team has agreed to provide DMS read-only access to the Billing & Collections database. DMS will have the ability to create queries against the database. In order to facilitate the query process, DMS would like to purchase a reporting front end, such as Crystal Reports. | This change request has been closed because it can be satisfied with the existing adhoc report request process. | N/A | Ticket was updated and closed with the following text (request was submitted by DMS): This change request has been closed because it can be satisfied with the existing adhoc report request process.
32 | User Queue Report | Reporting | Currently, MFMP doesn’t have the functionality to provide a report that shows the amount of time it takes for individual user to approve a transaction. This report would help meet prompt payment requirements by identifying users who are not approving their transactions in a timely manner. DMS has requested that MFMP develop the functionality to provide a report that will allow agencies to track how long it takes individual user in the approval flow or a group of user to approve transactions. |  | 2007-10-25
213104 | Faith-based organizations | Ariba Buyer | Currently, MFMP does not collect any info regarding the provider's status as a faith based organization. The agency would like to know what it would it take to add the collection of this information in the vendor registration process. This has been an area of special interest and we regularly receive questions dealing with this category of provider. Currently there is no easy way of collecting the information. | We have confirmed with the requesting agency that this functionality is no longer needed. | N/A | This ticket has been closed per request of the agency.
286591 | Part # for ASN invoices | Invoicing | When vendors submit invoices electronically, vendors cannot submit the part number. This could cause the agency to contact the vendor directly for the part number and is not an efficient process. | This change request was closed by SIR 710. | 2007-12-20 | Ticket was updated and closed with the following text (request was submitted by DMS): The Change Review Board (CRB) reviewed and approved the following recommendation for this change request at the meeting held on January 31st. Please contact BuyerHelp (BuyerHelp@myfloridamarketplace.com) with any questions. This change request should be closed since SIR 710 was created for this issue. SIR 710 was resolved in the 8.6 Release (December 2007).
286586 | Duplicate invoice checking | Invoicing | Duplicate invoice checking for invoices submitted electronically does not occur until the Invoice Reconciliation is created. If the IR is a duplicate then the user must reject the invoice. | DMS has withdrawn this change request as it is not technically feasible. DMS is recommending that a report request be submitted. | N/A | Ticket was updated and closed with the following text (request was submitted by DMS): DMS has withdrawn this change request as it is not technically feasible. DMS is recommending that a report request be submitted.
213128 | Contact Name on STC Master Agreements | Contracts | Inside a Master Agreement (MA) there is a contact for every MA listed in MFMP. The contact name listed for a majority of the State Term Contract MAs is incorrect. Instead of going through a process of changing each STC MA, it is better to make hide this contact. With this CR being implemented into MFMP prevents buyers from trying to reach out to the incorrect person. If a buyer needs to obtain the STC administrator they can obtain the contact person by clicking on the STC # link located on the MA. | DMS withdraws this change request. DMS will discuss changing existing STC contacts with State Purchasing. |  | Ticket was updated and closed with the following text (request was submitted by DMS): DMS withdraws this change request. DMS will discuss changing existing STC contacts with State Purchasing.
213200 | Hide unused Analysis fact selections | Reporting | When creating an Analytical report, the fact tables which are not populated by the base loads should be hidden from selection. These fact tables would contain no relevant data therefore should not be presented to the user for use. | DMS recommends this CR should be closed. SIR 813 was created for suppliers and commodity codes being displayed as "unclassified." A new SIR would be opened for any additional "unclassified" fields. | N/A 1/31/08: CRB Confirmed to closed this CR | Ticket was updated and closed with the following text (request was submitted by DMS): The Change Review Board (CRB) reviewed and approved the following recommendation for this change request at the meeting held on January 31st: This CR should be closed. SIR 813 was created for suppliers and commodity codes being displayed as "unclassified." A new SIR would be opened for any additional "unclassified" fields.
213124 | Update PO Terms of Use file | Ariba Buyer | Customers would like the MFMP T&Cs to either reflect PO (purchase order) or DO (direct order) but not both. Currently, the T&C read both. Statute 287 refers to PO. | DMS recommends that this change request be closed. This change request is no longer valid. MFMP maintains a link to the terms and conditions (http://marketplace.myflorida.com/vendor/po_tou.pdf). This document contains only references to "PO" or purchase order. | N/A 1/31/08: CRB Confirmed to closed this CR | Ticket was updated and closed with the following text (request was submitted by DMS): DMS recommends that this change request be closed. This change request is no longer valid. MFMP maintains a link to the terms and conditions (http://marketplace.myflorida.com/vendor/po_tou.pdf). This document contains only references to "PO" or purchase order.
213125 | Add Commodity Code | Ariba Buyer | Customers request that an additional commodity code for Freight. This commodity code should not start with a class of (9XX). This customer needs to add an additional line item for freight and reports that there is no valid commodity code. | DMS recommends that this change request be closed. This change request could be accomplished by State Purchasing requesting an ODU to add a commodity code. | N/A 1/31/08: CRB Confirmed to closed this CR. However the MFMP team will take action by discussing with State Purchasing (SP) the need to add an additional commodity code. Upon agreement by SP, an ODU will then be submitted for inclusion in MFMP. | Ticket was updated and agency contacted with the following text: The Change Review Board (CRB) reviewed and approved the following recommendation for this change request at the meeting held on January 31st. Please contact BuyerHelp (BuyerHelp@myfloridamarketplace.com) with any questions. This change request could be accomplished by State Purchasing requesting an ODU to add a commodity code. The MFMP team will take action by discussing with State Purchasing (SP) the need to add an additional commodity code.
213126 | Add Unit of Measure to Receiving Page | Ariba Buyer | Customers request that a Unit of Measure be added to the receiving page. The customer states that the agency often receives different types of units and that quantity does not always provide an accurate description of what was received. An example cited was that if a case of X was ordered, which was comprised of 12 boxes, and only 4 boxes came in, there is no way to receive the 4 boxes. The agency can receive 33 percent of the order, but this cannot be easily identified. | DMS recommends that this change request be closed. Unit of measure is driven from the purchase order. | N/A 1/31/08: CRB Confirmed to closed this CR | Ticket was updated and agency contacted with the following text: The Change Review Board (CRB) reviewed and approved the following recommendation for this change request at the meeting held on January 31st. Please contact BuyerHelp (BuyerHelp@myfloridamarketplace.com) with any questions. This change request should be closed. Unit of measure is driven from the purchase order.
222247 | Attachments Tab | Ariba Buyer | In place of DFS and agencies having to search different places for attachments required for payment documentation why not have a "Attachment" tab like the order, receipts, approval flow, etc. so that all attachments whether made from the purchasing group or the fiscal office all are within one location place in MFMP system. DFS rejects payment requests on not being able to find where the backup to support payment is within several options available for attachments. With one attachment button regardless of what queue your in (direct orders, pr's or invoice reconciliation) that would attach all documents in one location in place of several would cut down on audit reviews for agencies to process payments and cut down on DFS time in searching for location of which queue the document resides in. | DMS recommends this change request be closed. This change request is not technically feasible. The tabs listed on each type of approvable are part of the Ariba core functionality. | N/A 1/31/08: CRB Confirmed to closed this CR | Ticket was updated and agency contacted with the following text: The Change Review Board (CRB) reviewed and approved the following recommendation for this change request at the meeting held on January 31st. Please contact BuyerHelp (BuyerHelp@myfloridamarketplace.com) with any questions. This change request should be closed. After further evaluation, this change request is not technically feasible. The tabs listed on each type of approvable are part of the Ariba core functionality.
250428 | Edits to Catalog Line Items | Ariba Buyer | Currently when a Requester uses the Catalog Tab to enter information and create a requisition and it reaches Purchasing, the Purchasing Bureau is unable to make significant changes to the line item. Specifically, changing the dollar amount or other information. Purchasing agents can only change quantity at this time. Since items cannot be modified, the requestor has to withdraw the requisition and resubmit after removing and re-adding the line item in question as a non-catalog item. Purchasing would like the ability to make changes to catalog tab items. Sometimes it is necessary for Purchasing Agents to modify PR's from the catalog. Without the ability to modify PR's from the Catalog, unlike Non-catalog items, the request has to be withdrawn, since it cannot go any further in the process. The Purchasing role can be modified to allow for it to make changes to the Catalog items. | DMS recommends this change request be closed. This is not a recommended purchasing practice. | N/A 1/31/08: CRB Confirmed to closed this CR | Ticket was updated and agency contacted with the following text: The Change Review Board (CRB) reviewed and approved the following recommendation for this change request at the meeting held on January 31st. Please contact BuyerHelp (BuyerHelp@myfloridamarketplace.com) with any questions. This change request should be closed. This is not a recommended purchasing practice.
254982 | Org Drop Down | Ariba Buyer | When a user is added to the MyFloridaMarketPlace system, we assign an org. level – then the user creates a requisition and needs to spend out of an org. code that they don’t have access to. A requester is added for the org. code in question and the requester changes the information required and a DO is issued. Moving forward the user now has the org. code in question in the drop down box now for future use – which they shouldn’t be able to do. DEP doesn’t consider this an enhancement but a functionality problem. We set org. levels for a reason – we do not want a user being able to choose an org. code that is not within the org. level – so I assume the fix would be to do away with the drop down boxes on the accounting screen altogether. | DMS recommends this change request be closed and address concern as a part of training. | N/A 1/31/08: CRB Confirmed to closed this CR | Ticket was updated and agency contacted with the following text: The Change Review Board (CRB) reviewed and approved the following recommendation for this change request at the meeting held on January 31st. Please contact BuyerHelp (BuyerHelp@myfloridamarketplace.com) with any questions. This change request should be closed. This concern can be addressed as a part of training.
272865 | Dollar Amt Split Displayed on DO Print | Ariba Buyer | Currently in MFMP, when split accounting on a line item is done by dollar amount rather than by percentage, it is shown in the detail of the line. However, when you print the DO, the hardcopy will not show the split by dollar amount like it was requested and shown in MFMP. The hardcopy shows the split as a calculated percentage rather than the chosen dollar amount when printed. It appears to be a deviation from what was intended by choice of splitting a line item by either dollar amount or percentage. Whether viewing the DO from your PC or a printed hardcopy the split accounting information should provide the chosen format of percentage or dollar amount. Other requestors or auditors that may not have access to MFMP but need to see DO information under the current format would review incorrect accounting information once the DO is printed for them. Currently, when split accounting is chosen by percentage on a line item, it prints that way on the DO. Why would it not follow through with that same process when chosen to be split by dollar amount? | DMS recommends that this change request be closed. This functionality can be provided by paying through MFMP. | N/A 1/31/08: CRB Confirmed to closed this CR | Ticket was updated and agency contacted with the following text: The Change Review Board (CRB) reviewed and approved the following recommendation for this change request at the meeting held on January 31st. Please contact BuyerHelp (BuyerHelp@myfloridamarketplace.com) with any questions. This change request should be closed. This functionality can be provided by paying through MFMP.
290912 | Encrypt p-card number on DO's | Ariba Buyer | We are concerned that DO's sent to vendor via e-mail do not have the p-card number encrypted. If not, this issued should be reviewed by DFS/DMS to determine if this is in compliance with state policy concerning p-card usage. | DMS recommends this change request be closed. | N/A 1/31/08: CRB Confirmed to closed this CR | Ticket was updated and agency contacted with the following text: The Change Review Board (CRB) reviewed and approved the recommendation to close this change request at the meeting held on January 31st. Please contact BuyerHelp (BuyerHelp@myfloridamarketplace.com) with any questions.
293136 | Ability to create change order while IR is pending FLAIR | Ariba Buyer | Currently, when attempting to issue a change order, the change cannot be completed until all invoices are in “paid” status. The current “work-around” is that you have to call F&A and make certain they are not currently processing invoices against that particular PO. This stops the procurement office from making the required changes to the purchase order that are necessary for the requester and it stops F&A staff from being able to process invoices to comply with prompt payment laws. Not allowing this dual action has resulted in loss of grant funds and has had impact on end of fiscal year procurements. | DMS recommends this change request be closed as this does not comply with recommended business processes. | N/A 1/31/08: CRB Confirmed to closed this CR | Ticket was updated and agency contacted with the following text: The Change Review Board (CRB) reviewed and approved the following recommendation for this change request at the meeting held on January 31st. Please contact BuyerHelp (BuyerHelp@myfloridamarketplace.com) with any questions. This change request should be closed as this does not comply with recommended business processes.
307636 | Print Central Receiver queue | Ariba Buyer | We have several users that function as central receivers for an entire county health department. In the previous version of MFMP, they were able to search and print a complete list of orders pending receipt, known as the "receiving queue". The users went to the "swoosh" screen and clicked "receive". On the "Select Request" page, they left the search box empty and clicked on "Search". The "Search Results" were displayed. They would click the print icon on the tool bar and the entire list would print. The information needed was Order ID, Title, Dare Created, Status and Supplier. The list was used to follow up on outstanding orders, and the number of records usually is more than 1,000. With the new version of MFMP, they are not able to print the entire list, only those lines displayed in the window visible on the screen. There is no export function on the screen. | MFMP will confirm this issue. DMS recommends this change request be closed. This issue can be addressed as a training topic. 1/29/08 Research Completed: Print of Queue cannot be accomplished in 2.0. DMS concurs that this change request be closed. | N/A 1/31/08: CRB Confirmed to closed this CR | Ticket was updated and agency contacted with the following text: The Change Review Board (CRB) reviewed and approved the following recommendation for this change request at the meeting held on January 31st. Please contact BuyerHelp (BuyerHelp@myfloridamarketplace.com) with any questions. This change request should be closed. This concern can be addressed as a part of training.
311560 | Ship-to link display acutal address | Ariba Buyer | Prior to the MFMP 2.0 upgrade, the Ship To address was visible by clicking the Ship To link. After the upgrade, clicking the Ship To link no longer displays the actual address associated with the Ship To ID. Actual Ship To address needs to be visible to requesters and approvers of a request to ensure that the correct address is being provided to the vendor. When this information is not available, potential issues regarding shipping are more prone to occur. If the ship to address is incorrect, both financial and workload burdens are placed on the Department to correct this. This request is to have the Ship To address link show the actual address associated with the ID number when a user clicks the link. | MFMP will confirm this link was available in the 7.1a version to determine if a SIR should be created. MFMP will confirm the ship to is a link in 2.0. 1/29/08 Research Completed: SIR 872 created. CR can be closed. | N/A 1/31/08: CRB Confirmed to closed this CR | Ticket was updated and agency contacted with the following text: The Change Review Board (CRB) reviewed and approved the following recommendation for this change request at the meeting held on January 31st. Please contact BuyerHelp (BuyerHelp@myfloridamarketplace.com) with any questions. This change request should be closed since SIR 872 was created for this issue. SIR 872 was resolved in the 8.8 Release (February 2008).
234378 | Sourcing "Items" Section | Sourcing | Disable the module within the sourcing tool that will not permit an RFx launch unless there is a minimum of one entry in the "Items" section. | DMS recommends this change request be closed. This change request is not technically feasible. This limitation is a result of Ariba core functionality for all events except for RFI's (Request for Information). | N/A 1/31/08: CRB Confirmed to closed this CR | Ticket was updated and agency contacted with the following text: The Change Review Board (CRB) reviewed and approved the following recommendation for this change request at the meeting held on January 31st. Please contact BuyerHelp (BuyerHelp@myfloridamarketplace.com) with any questions. This change request should be closed. After futher evaluation, this change request is not technically feasible. This limitation is a result of Ariba core functionality for all events except for RFI's (Request for Information).
213122 | Allow the Vendor to capture Dunns Number on Vendor Reg | Vendor Registration | Customers have requested that the vendors have the ability to enter the Dunns number into Vendor Reg. This functionality will give the vendors an efficient method for tracking their Dunns number when they receive it. This will also allow Vendor Reg the ability to track all important information that may be required by MyFloridaMarketPlace. | DMS would like to clarify this is still requested functionality. | N/A 1/31/08: CRB Confirmed to closed this CR | Ticket was updated and closed with the following text (request was submitted by Chuck Bruce): The Change Review Board (CRB) reviewed and approved the following recommendation for this change request at the meeting held on January 31st. Please contact BuyerHelp (BuyerHelp@myfloridamarketplace.com) with any questions. This change request should be closed.
23 | Level 2 integration | Ariba Buyer | Currently, one FLAIR password is set-up in order to create encumbrances in FLAIR through MFMP. Each entity/PUI combination is provided one FLAIR username and password at the Level 1 security level only. This causes an issue for DOAH and FSDB because these are dotted-line agencies and access FLAIR at Level 2 or lower, never at Level 1. DMS has requested that a change be made to the MFMP/FLAIR encumbrance interface to allow agencies to access FLAIR at the Level 2 access. |  | 2007-12-26
39 | OSD - Automation | Vendor Registration | Establishment of a two way interface between OSD and the MFMP Vendor database that encompasses data changes that relates to vendor information for minority and women owned businesses that are both general in nature (name and address) and specific to the minority subject matter. |  | 2008-04-07
37 | Mass edit functionality for the Purchasing Code and Method of Procurement fields | Ariba Buyer | Mass edit functionality for the Purchasing Code and Method of Procurement fields on the requisition |  | 2008-05-29
46 | Method of Procuremeent Updates | Ariba Buyer | The existing MOP codes may not be applicable for all agencies (for example, codes F, H, I, J and O do not include references to Florida Statute 255.0525). The list of MOP codes should be updated so that agencies can reference the appropriate type of purchase. |  | 2008-05-29
44 | Legislative data scoping | Ariba Buyer | The Department of Management Services (DMS) currently has a plan to sunset the Statewide Purchasing System (SPURS) application. There is one remaining entity that is using the purchase order functionality of SPURS - the Florida Legislature. The Legislature has requested that their data be scoped so that it is not visible by other agencies in MFMP. |  | 2008-09-25
45 | Add Service-Disabled Veteran as CMBE classification | Vendor Registration | With the passing of legislation (HB 687), service-disabled veterans will be considered a Florida CMBE. Changes will be required for several MFMP applications (VRS, Buyer, interfaces). |  | 2008-10-29
50 | Vendor Password Reset | Vendor Registration | Currently, any user who has lost or forgotten his password needs to call the help desk to have the password reset to the user's Tax ID. This approach is inefficient, because it requires manual intervention by help desk staff. The enhancement will allow users to request and execute password resets through interaction with the system and email correspondence. |  | 2009-01-25
36 | Make the Enc number the DO number | Ariba Buyer | When the encumbered requisition is fully approved and an order is generated, a DO number will be assigned starting with “DO” and then appending the encumbrance number. Encumbered and unencumbered requisitions will use the same incremental counter to reduce the frequency of creating duplicate DO numbers. |  | 2009-02-25
47 | SPURSView line item descrption | Ariba Buyer | Currently, MFMP does not send the line item description information to DMS to display in SPURSView. Since this is the public portal and vendors often use SPURSView to view DO information, it would be helpful if MFMP sent this data to DMS so it could be displayed with the rest of the DO information in SPURSView. |  | 2009-04-28
51 | Request to add vendor inactivation reason code in Vendor Reg | Vendor Registration | During SPURS sunset discussions, DFS has requested that MFMP add an inactivation reason code in the Vendor Registration system that would indicate the reason a vendor's registration (or location) is being inactivated. This inactivation reason code would then be passed to FLAIR in the nightly MFMP to FLAIR vendor interfaces for updates on the statewide vendor file. |  | 2009-04-28